## Slide 1
CBF System Configuration Status Introduce
BOS Cloud 2026-05-13

## Slide 2
Agenda
1 Basic Requirements for System CBF (parallel line system)
2 Introduction to the Configuration Status of Each Module
3 Introduction to the testing scope of each module( MM & SD ONLY )
4 Assign the National chart of Account (See the details)
5 Configure the Tax code of CBF (Excel sheet)

## Slide 3
1 Basic Requirements for System CBF (parallel line system)
Basic Requirements for System CBF (parallel line system) |  |  |  |  | 
NO. | Content | Status | Completion | comment | PIC
1 | 客户组织架构图 - 系统搭建基础信息 | finished | 100% |  | 
 | Customer Organization Chart – Basic Information for System Setup |  |  |  | 
2 | 物料主数据 | in progress | 10% | tempate ok, no data now | 
 | Material Master Data |  |  |  | 
3 | 客户主数据（全字段） | in progress | 10% | tempate ok, no data now | 
 | Customer Master Data (Full Fields) |  |  |  | 
4 | 供应商主数据（全字段） | in progress | 10% | tempate ok, no data now | 
 | Vendor Master Data (Full Fields) |  |  |  | 
5 | 期初库存迁移数据表 | in progress | 10% | tempate ok, no data now | 
 | Opening Inventory Migration Data Sheet |  |  |  | 
6 | 客商统御科目设计 | in progress |  |  | 
 | Reconciliation Account Design for Customers & Vendors |  |  |  | 
7 | 物料账务处理 - MM 科目设计 | in progress |  |  | 
 | Material Accounting Processing – MM Account Design |  |  |  | 
8 | 客户税分类逻辑和结构 | in progress |  |  | 
 | Customer Tax Classification Logic and Structure |  |  |  | 
9 | 客户分配组和物料分配组设计 | in progress |  |  | 
 | Customer Account Assignment Group & Material Account Assignment Group Design |  |  |  | 
10 | 采用销售订单 BOM活动类型设计 | in progress |  |  | 
 | Sales Order BOM Adoption & Activity Type Design |  |  |  | 
11 | 基础会计科目表 - 系统 YCOA+NA | in progress | 100% |  | 
 | Basic Chart of Accounts – System YCOA + NA |  |  |  | 

## Slide 4
Configuration Status of Each Module |  |  |  |  |  |  | 
NO. | TIME | MODULE | PIC | CONFIG COMPLETE PART | UNCONFIG PART | Percentage completed | Confirm Point
1 | 2026/5/12 | MM | ERIC | 1 organizational structure config finished . 2 bp config finished . 3 material config finished. 4 warehouse config finished. 5 basic MM module function was smoothly test | some special process like Subcontracting , return back config not yet. | 80% | To be checked
2 | 2026/5/12 | SD | Allen Chen | 1 Sales enterprise structure configuration has been 100% completed. 2 other sales functions configuration have been 90% done, except the BP part & revenue account determination | BP part & revenue account determination | 90% | To be checked
3 | 2026/5/12 | FICO | Wang Huan | 1 The configuration related to the Chart of Accounts, Company Code, Controlling Area, Cost Elements, Cost Centers, Profit Centers, Material Ledger, and FI-CO integration has been completed. 2 None. All FICO-related configurations are fully completed. 100% All configurations have been completed and confirmed. | none | 100 | None
2 Introduction to the Configuration Status of Each Module

## Slide 5
Set Up Organizational Structure-5100

## Slide 6
Test Case ID | Module | Test Case Name* | [Scope GUID] | [Solution Process Name] | [Test Case Priority] | [Test Case Owner] | Test Case Status | Action Title* | Action Instructions* | Action Staus
1 | MM | Requisitioning (18J) | 18J | Create Purchase Requisition | high | TBD | In Preparation | xxxx.PPT | follow the sap satndard test script as 18J | PASS/NG
2 | MM | Procurement of Direct Materials (J45) | J45 | Create Purchase Order (with Direct Materials) | high | TBD | In Preparation |  |  | 
3 | MM | Consumable Purchasing (BNX) | BNX | Convert Purchase Requisition to Purchase Order | high | TBD | In Preparation |  |  | 
4 | MM | Subcontracting (BMY) | BMY | Create Supplier Invoice | high | TBD | In Preparation |  |  | 
5 | MM | Procurement of Services (22Z) | 22Z | Create Purchase Requisition(Standard Procurement of Service) | high | TBD | In Preparation |  |  | 
6 | MM | Return to Supplier (BMK) | BMK | Create Credit Memo | high | TBD | In Preparation |  |  | 
7 | MM | Physical Inventory – Inventory Count and Adjustment (BML) | BML | Create Physical Inventory Documents (Mass Creation) | high | TBD | In Preparation |  |  | 
8 | SD | Mass Load and Mass Maintenance for Business Partner (1RK) | 1RK | Manage customer/payer/ship-to/plant master data | high | TBD | In Preparation |  |  | 
9 | SD | Sales Inquiry (1IQ) | 1IQ | Manage sales inquiry process | high | TBD | In Preparation |  |  | 
10 | SD | Sales Quotation (BDG) | BDG | Manage sales quotation process | high | TBD | In Preparation |  |  | 
11 | SD | Sell from Stock (BD9) | BD9 | Manage sales order (sell from stock) process - sales order ->outbound delivery->billing | high | TBD | In Preparation |  |  | 
12 | SD | Free of Charge Delivery (BDA) | BDA | Manage free of charge sales process - sales order ->outbound delivery ->billing (if in need) | high | TBD | In Preparation |  |  | 
13 | SD | Credit Memo Processing (1EZ) | 1EZ | Manage sales credit memo process | high | TBD | In Preparation |  |  | 
14 | SD | Debit Memo Processing (1F1) | 1F1 | Manage sales debit memo process | high | TBD | In Preparation |  |  | 
15 | SD | Lean Customer Returns (BDD) | BDD | Manage sales return process | high | TBD | In Preparation |  |  | 
16 | SD | Sale of Services (2EQ) | 2EQ | Manage service sales process | high | TBD | In Preparation |  |  | 
17 | SD | Sales Order Processing for Non-Stock Material (2ET) | 2ET | Manage non-stock sell process | high | TBD | In Preparation |  |  | 
18 | SD | Basic Credit Management (BD6) | BD6 | Credit manage process | high | TBD | In Preparation |  |  | 
3 Introduction to the testing scope of each module( MM&SD ONLY )

## Slide 7
Assign Chart of Accounts by National COA

## Slide 8
Assign Chart of Accounts by National COA

## Slide 9
Thank you