## Hengtian_Menfushi Germany Bi-w
Bi-weekly rolling plan for the 13th week of 2026 |  | Planned start date
2026-03-23
serial number | Task Description | Subtask Description | Deliverables/Main tasks | Way | person in charge | Participants | Work location | Planned start date | time | Planned end date | time | Completed status
1 | Development Program DEMO | ZS00 Function Demo | Meeting Minutes | remote | Zhang Junbo, Hu Xinran | Fan Renwen, Zhang Jiayu, Ute, Zhang Junbo, Hu Xinran | teams meeting | 2026-03-23 | 9:00 | 2026-03-23 | 18:00 | Completed
2 |  | HU+Bar code feature demo | Meeting Minutes | remote | Zhang Junbo, Hu Xinran | Fan Renwen, Zhang Jiayu, Ute, Zhang Junbo, Hu Xinran | teams meeting | 2026-03-24 | 14:10 | 2026-03-24 | 18:00 | Completed
3 |  | DMS document implementation solution communication | Meeting Minutes | remote | Zhang Junbo, Hu Xinran | Fan Renwen, Zhang Jiayu, Ute, Zhang Junbo, Hu Xinran | teams meeting | 2026-03-24 | 14:10 | 2026-03-24 | 18:00 | Completed
4 |  | ZEPL feature demo | Meeting Minutes | remote | Zhang Junbo, Hu Xinran | Fan Renwen, Zhang Jiayu, Ute, Zhang Junbo, Hu Xinran | teams meeting | 2026-03-25 | 9:15 | 2026-03-25 | 12:00 | Completed
5 |  | ZCS02 Function Demo | Meeting Minutes | remote | Zhang Junbo, Hu Xinran | Fan Renwen, Zhang Jiayu, Ute, Zhang Junbo, Hu Xinran | teams meeting | 2026-03-25 | 14:10 | 2026-03-25 | 18:00 | Completed
6 |  | Custom form printing development communication | Meeting Minutes | mail | Zhang Junbo, Hu Xinran | Fan Renwen, Zhang Jiayu, Ute, Zhang Junbo, Hu Xinran | teams meeting | 2026-03-26 | 9:15 | 2026-03-26 | 11:00 | Completed
7 | Test material import | Test system material import | Data import | remote | Zhang Junbo, Yan Hongye | Zhang Junbo, Yan Hongye | Nanjing | 2026-03-23 | 9:00 | 2026-04-02 | 18:00 | in progress
| Customer import | Customer import test system | Data import | remote | Zhang Junbo | Zhang Junbo | Nanjing | 2026-03-23 | 9:00 | 2026-04-02 | 18:00 | Completed
| Static data template export | Exporting Procurement Information Records | Data list | remote | Fan Renwen, Zhang Jiayu, Zhang Junbo | Fan Renwen, Zhang Jiayu, Zhang Junbo | teams meeting | 2026-03-31 | 9:00 | 2026-04-08 | 18:00 | Completed
|  | BOM Export | Data list | remote | Fan Renwen, Zhang Jiayu, Zhang Junbo | Fan Renwen, Zhang Jiayu, Zhang Junbo | teams meeting | 2026-03-31 | 9:00 | 2026-04-08 | 18:00 | Completed
|  | Process route derivation | Data list | remote | Fan Renwen, Zhang Jiayu, Zhang Junbo | Fan Renwen, Zhang Jiayu, Zhang Junbo | teams meeting | 2026-03-31 | 9:00 | 2026-04-08 | 18:00 | Completed
|  | Correlation Allocation Derivation | Data list | remote | Fan Renwen, Zhang Jiayu, Zhang Junbo | Fan Renwen, Zhang Jiayu, Zhang Junbo | teams meeting | 2026-03-31 | 9:00 | 2026-04-08 | 18:00 | Completed
8 | Programming | ZPP_SC Evaluation of Changes (Drawing) Development | FS | remote | Zhang Junbo, Chen Zengfeng | Zhang Junbo, Chen Zengfeng | Nanjing | 2026-03-25 | 9:00 | 2026-03-31 | 18:00 | Completed
9 |  | ZPP_STPO_AEND Evaluation of changes in BOM_FS written | FS | remote | Zhang Junbo | Zhang Junbo | Nanjing | 2026-03-30 | 9:00 | 2026-04-05 | 18:00 | Completed
10 |  | DMS document functionality development | FS | remote | Zhang Junbo, Guo Zhipeng | Zhang Junbo, Guo Zhipeng | Nanjing | 2026-03-30 | 9:00 | 2026-04-05 | 18:00 | in progress
11 | Form printing | Print templates provided | mail | remote | Ute | Zhang Junbo | teams meeting | 2026-03-30 | 9:00 | 2026-04-05 | 18:00 | Completed
12 | Static data collection | Procurement information record data | Data list | remote | Ute | Zhang Junbo, Fan Renwen, Zhang Jiayu | teams meeting | 2026-03-31 | 9:00 | 2026-04-10 | 18:00 | in progress
13 |  | BOM data | Data list | remote | Ute | Zhang Junbo, Fan Renwen, Zhang Jiayu | teams meeting | 2026-03-31 | 9:00 | 2026-04-10 | 18:00 | in progress
14 |  | Process route data | Data list | remote | Ute | Zhang Junbo, Fan Renwen, Zhang Jiayu | teams meeting | 2026-03-31 | 9:00 | 2026-04-10 | 18:00 | in progress
15 |  | Correlation allocation data | Data list | remote | Ute | Zhang Junbo, Fan Renwen, Zhang Jiayu | teams meeting | 2026-03-31 | 9:00 | 2026-04-10 | 18:00 | in progress
16 | Importing static template data | Exporting Procurement Information Records | Data import | remote | Zhang Junbo | Zhang Junbo, Fan Renwen, Zhang Jiayu | Nanjing | 2026-04-13 | 9:00 | 2026-04-17 | 18:00 | in progress
17 |  | BOM Export | Data import | remote | Zhang Junbo | Zhang Junbo, Fan Renwen, Zhang Jiayu | Nanjing | 2026-04-13 | 9:00 | 2026-04-17 | 18:00 | Completed
18 |  | Process route derivation | Data import | remote | Zhang Junbo | Zhang Junbo, Fan Renwen, Zhang Jiayu | Nanjing | 2026-04-13 | 9:00 | 2026-04-17 | 18:00 | in progress
19 |  | Correlation Allocation Derivation | Data import | remote | Zhang Junbo | Zhang Junbo, Fan Renwen, Zhang Jiayu | Nanjing | 2026-04-13 | 9:00 | 2026-04-17 | 18:00 | in progress
20 | Development Program DEMO | ZPP_STPO_AEND series of programs | Meeting Minutes | remote | Zhang Junbo | Zhang Junbo, Fan Renwen, Zhang Jiayu, Ute | teams meeting | 2026-04-13 | 9:00 | 2026-04-17 | 18:00 | Completed
21 | Development Program DEMO | DMS Function Demonstration | demo | remote | Zhang Junbo | Zhang Junbo, Fan Renwen, Zhang Jiayu, Ute | teams meeting | 2026-04-21 | 9:00 | 2026-04-21 | 18:00 | in progress
22 | User Management Training | System training | User Manual | remote | Zhang Junbo | Zhang Junbo, Fan Renwen, Zhang Jiayu, Ute | teams meeting | 2026-04-21 | 9:00 | 2026-04-21 | 18:00 | in progress
23 | ZMM_BANF_COCKPIT | FS writing | FS | remote | Zhang Junbo | Zhang Junbo | Nanjing | 2026-04-21 | 9:00 | 2026-04-25 | 18:00 | in progress
24 | Sales order printing template development | Programming | FS | remote | Zhang Junbo | Zhang Junbo | Nanjing | 2026-04-21 | 9:00 | 2026-04-30 | 18:00 | in progress
25 | Importing static template data | Exporting Procurement Information Records | Data import | remote | Zhang Junbo | Zhang Junbo | Nanjing | 2026-04-21 | 9:00 | 2026-04-28 | 18:00 | in progress
26 |  | Process route derivation | Data import | remote | Zhang Junbo | Zhang Junbo | Nanjing | 2026-04-21 | 9:00 | 2026-04-28 | 18:00 | in progress
27 |  | Correlation Allocation Derivation | Data import | remote | Zhang Junbo | Zhang Junbo | Nanjing | 2026-04-21 | 9:00 | 2026-04-28 | 18:00 | in progress
28 |  | Material data import | Data import | remote | Zhang Junbo | Zhang Junbo | Nanjing | 2026-04-21 | 9:00 | 2026-04-28 | 18:00 | in progress
29 | Test sample data provided | Data export | Data export | remote | Ute | Ute | teams meeting | 2026-04-21 | 9:00 | 2026-04-28 | 18:00 | Completed
30 | System Process Demo | Get the 8520/8530 end-to-end process from sales to production to procurement to warehouse up and running | demo | remote | Zhang Junbo | Ute | Nanjing | 2026-04-24 | 9:00 | 2026-05-06 | 18:00 | in progress
31 | Print Form Development Communication | Users need to give an actual demonstration to explain the business background of printing, as well as the value retrieval logic and format requirements | demo | remote | Ute | Zhang Junbo, Fan Renwen, Zhang Jiayu, Ute | teams meeting | 2026-04-24
Note on C2: annotation: hyalman: Please enter the date for next Monday. - Daniel - Liu Peng - Liu Peng