## 问题清单
Priority /优先级 | Task Description / 任务描述 | Subtask Description / 子任务描述 | Responsible Person / 负责人 | Participants / 参与人 | Deadline / 截止完成日期 | Completion Status / 完成状态 | Remarks / 备注
1 | Static data collection / 静态数据收集 | BOM master data / BOM主数据 | Ute | 范仁文、张嘉瑜、Ute、张俊波、胡欣然 |  |  | Waiting for German user to export data for validation – Zhongshan team support / 待德国用户导出数据进行验证-中山团队支持
|  | Routing / 工艺路线 | Ute | 范仁文、张嘉瑜、Ute、张俊波、胡欣然 |  |  | Waiting for German user to export data for validation – Zhongshan team support / 待德国用户导出数据进行验证-中山团队支持
|  | Production version / 生产版本 | 张俊波 | 范仁文、张嘉瑜、Ute、张俊波、胡欣然 |  |  | Waiting for German user to export data for validation – Zhongshan team support / 待德国用户导出数据进行验证-中山团队支持
|  | Purchasing info record / 采购信息记录 | Ute | 范仁文、张嘉瑜、Ute、张俊波、胡欣然 |  |  | Waiting for German user to export data for validation – Zhongshan team support / 待德国用户导出数据进行验证-中山团队支持
|  | Customer/vendor master data / 客商主数据 | Ute | 范仁文、张嘉瑜、Ute、张俊波、胡欣然 |  |  | Waiting for Monforts Germany to verify data integrity in test system / 待门富士德国验证测试系统数据完整性
|  | Material master data / 物料主数据 | Ute | 范仁文、张嘉瑜、Ute、张俊波、胡欣然 |  |  | Waiting for Monforts Germany to verify data integrity in test system / 待门富士德国验证测试系统数据完整性
|  | VC relevance / VC相关性 | Ute | 范仁文、张嘉瑜、Ute、张俊波、胡欣然 |  |  | Waiting for German user to export data for validation – Zhongshan team support / 待德国用户导出数据进行验证-中山团队支持
|  | ECC data export program implementation in production system / ECC数据导出程序植入正式系统 | 门富士中山 | 范仁文、张嘉瑜、Ute、张俊波、胡欣然
2 | UAT | Simulate end-to-end business process testing & DEMO recording / 模拟端到端业务流程测试&DEMO录制 | 张俊波 | 范仁文、张嘉瑜、Ute、张俊波、胡欣然
3 | Program Validation /程序验证 | Program validation – Completed development programs need validation by German user in test system / 程序验证 - 已完成的开发程序德国用户需要测试系统中进行验证 | Ute | 范仁文、张嘉瑜、Ute、张俊波、胡欣然
4 | Program development / 程序开发 | ZMM_MAT series programs / ZMM_MAT系列程序 | 张俊波 | BOS开发团队 |  |  | Need to present business operation background in meeting with Monforts Germany / 需要德国门富士会议演示业务操作背景
|  | ZMEA function / ZMEA功能 | 张俊波 | BOS开发团队 |  |  | Need to present business operation background in meeting with Monforts Germany / 需要德国门富士会议演示业务操作背景
|  | ZMM_BANF_COCKPiT | 张俊波 | BOS开发团队 |  |  | Need to present business operation background in meeting with Monforts Germany / 需要德国门富士会议演示业务操作背景
|  | Series of business document print templates / 系列业务单据打印模版 | 张俊波 | BOS开发团队 |  |  | Need to clarify number of print items and corresponding business operations in meeting / 待会议明确需要打印的条目数，以及对应的业务操作
5 | Initial dynamic data collection / 期初动态数据收集 | Open production orders / 未清生产订单
Open purchase orders / 未清采购订单
Open sales orders / 未清销售订单